## Sheet1
P0 = crash bug, P1 = game stopping but not crash, P2 = not working as expected, P3 = annoying, P4 = nice to have, P5 = future release
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-02-12 | James | P2 | resolved | Kevin | The game wont render entities that are too far left When the window resolution increased to 1280x720, the renderer code was not changed, currently, x-pos must be >-125 in order to render | object should continue to be rendered when passing the left side | object disappears when touches x = -125 | shoot a bullet/bug towards the left side, and see it disappear
2 | 2024-02-12 | Kevin | P2 | resolved | Kevin | firing bullets in the wrong direction due to new camera centering (we translated origin of camera from top left to center) | bullet fire to mouse cursor | bullet fire in a random direction | click the mouse 1 button to fire -> bullet moves to positive x, positive y direction (from template 1)
3 | 2024-02-12 | Kevin | P2 | resolved | Kevin | player is faster than bullet due to movement system | when moving and shooting, bullet should be in front of player | bullet lags behind player | move up (W) -> position cursor above player -> hold mouse 1 to fire -> bullet is behind player
4 | 2024-02-12 | Kevin | P2 | resolved | Kevin | bullet is fired at old mouse position if mouse is not moved | bullets should fire towards mouse cursor when moving | bullet fires into old mouse position if mouse wasn't moved | move mouse -> hold fire (mouse 1) -> hold move up (W) -> stop moving mouse -> bullet velocity is relative to old mouse position
5 | 2024-02-13 | Kevin | P4 | resolved | Kevin | after being in mouse-cursor offset mode, and switching back, camera is stuck in offset | deactivating mouse-cursor offset mode should recenter camera back to player | camera is stuck in last camera position in mouse-cursor offset mode | press P -> move cursor around -> press P -> camera not centered on player
6 | 2024-02-13 | Kevin | P5 | resolved | Kevin | camera teleporting when mouse-cursor offset is activated and mouse position is anywhere but center | camera should transition to the point instead of teleporting | camera teleports to in between mouse cursor | move cursor somewhere -> press P -> move a tiny bit of the mouse -> camera teleports
7 | 2024-02-14 | Sam | P4 | resolved | Kevin | keep pressing the movement key while restart game, it can only recognize release and get opposite velocity without press anything | it does not move when we release | it move when we release | press D -> die to an enemy -> (game restarts) -> release D -> starts moving left
8 | 2024-02-15 | Kevin | P2 | resolved | Kevin | collision system sliding on the wall is jittery. when sliding beside the wall and spam movement to move towards the wall, it will jitter and sometimes stop the player | continues moving forwards without stopping or jitter when button is pressed | jittery and sometimes stops | go close to a long wall -> collide with it -> move parallel to the wall -> spam button to move towards the wall -> jitters and sometimes get stuck
9 | 2024-02-15 | Kevin | P2 | resolved | Kevin | entity collision on walls do not continue to wrap around the wall. not able to go forward | a wall is in front of you, you press and hold W to collide with object, hold S, it should go up because W is held | instead, even if W is held, system forgets that W is held even after there is no collisions/objects in front of player | object in front of player -> hold W -> collide -> hold S or D -> can't go around object
10 | 2024-02-16 | James | P4 | open |  | upon player death, player actions like firing, getting hit are still available. there is still a hit sound | player cannot attack, should not get hit, no music other than death sound | player is able to shoot bullets, get hit, and being hit sound is still playing | stay still -> die -> still get hit by bullet and hit sound plays
11 | 2024-02-16 | James | P4 | open |  | when constantly firing, death sound is not played | should stop firing sound when dead, and play the death soudn | firing sound still plays but death sound does not when player dies | Die while constantly firing
12 | 2024-02-16 | James | P4 | open |  | During player invunderability, other bullets pass through the player. | Bullets disapear upon collison under all circumastances but only take damage when not invunerable | Bullets pass through player when invunerable | Have 2 bullets hit the player in a short time span, shorter than the player invunerbility
13 | 2024-02-23 | Kevin | P1 | resolved | Kevin | game engine is rendering every single tile, which causes lag if the map is large | should not lag if world is large | it is lagging with massive frame drops | change world size to 30x30 or larger, upon starting the game, low framerates occur
14 | 2024-02-27 | Kevin | P3 | open |  | heart ui is disappearing due to new render optimization, in order to fix this, introduce renderrequest layers | hearts in ui should not disappear when zooming in to the max | heart disappears if zoomed in | zoom in -> hearts disappear
15 | 2024-03-01 | Alan | P2 | resolved | Kevin | Enemies can cross the wall rather than collide with it | enemy should collide with the wall and slide against it | enemy cross wall and glitches through it | start game -> wait for enemies to spawn and move towards the wall
16 | 2024-03-01 | Alan | P3 | open |  | FPS may drop when many enemies are generated. This may be caused by multiple direction calculation to player | game should not lag when there are many enemies on the screen | game lags when multiple enemies are on the screen | start game -> wait for enemies to spawn -> lag occurs when many enemies
17 | 2024-03-03 | Alan & Kevin | P2 | open |  | player can phase through anything and get to an unreachable position | player should be colliding with the wall after restoring window position | player teleports outside of the walls and over the walls | hold a direction key near a wall but don't collide with it -> click the window bar and drag it a little to freeze the screen -> unhold the mouse button -> player teleports to the other side
18 | 2024-03-03 | Kevin | P3 | open |  | since walls have half the collision, enemies can go into a wall tile and be stuck there | enemy should not be stuck and perhaps seek a path around the wall if current tile is a wall | enemy is stuck trying to get through the wall but can't due to collision | let enemy follow player -> go to a wall that has half collision box -> go to other side -> enemy can't move
19 | 2024-03-04 | Kevin | P3 | open |  | buggy ai. sometimes the path finding stops early when enemy can see the player, this results in it shooting the wall | enemy should not stop early and does not shoot the wall | problem could be from: can see player function. what happens is that in diagonal tiles, it assumes it is on the tile without considering offset. so it shoots the wall | make enemy follow to a wall in the middle -> go diagonal from it on the other side, it starts shooting the wall
20 | 2024-03-05 | Alan | P4 | resolved | Alan | Player being either bounce away from the wall or stuck in the wall when their collider is shifted | Player stops at the wall. Do not bounce off or stuck in the wall | Player being either bounce away from the wall or stuck in the wall when their collider is shifted | start game -> press wasd to walk to wall -> player collide the wall
21 | 2024-03-05 | Alan | P3 | open |  | player bullets are hitting the wall and disppearing when standing on the top tile | player bullet should shoot outside and not disappear | player bullet is disappearing when firing | walk to the top wall tile -> put mouse cursor below the player sprite -> hold left mouse button to fire -> bullet disappears
22